## Project Overview
Next-Cart Migration Project Toolkit
Bring scope, owners, risk, evidence, URL continuity, and launch decisions into one project view so the team can see what is ready and what still needs proof.
Start with the migration path, then work outward: plan accountable work, surface uncertainty early, validate evidence, protect priority URLs, and close launch decisions explicitly. Use current Next-Cart Documentation for procedures and exact service behavior; record project-specific choices and evidence here.
Plan | Risks | Validation | Redirects | Decisions | Overview / readiness
Project identity and migration
Project Name | Example Retail Replatforming |  |  | Project ID | NC-EX-2026-001
Source Platform | Magento 2 |  |  | Target Platform | Shopify
Migration Path |  |  |  | Supported Data Reference
Migration Service | Managed Service |  |  | Entity Points Plan | Pro+
Purchased Add-ons | Data Filter; Advanced Data Mapping |  |  | Purchased Entity Points | 16000
Approved Customization | CUST-01: agreed non-standard handling for legacy loyalty identifiers outside supported Standard Add-on scope. |  |  | Service Expiry
Project Owner | Customer Project Lead |  |  | Launch Approver | Executive Sponsor
Evidence Repository | Secure project workspace / migration-example |  |  | Next-Cart Contact | Next-Cart Migration Specialist
Milestones and control
Demo Migration planned date | 2026-08-03 |  |  | Full Migration planned date | 2026-08-17
Launch window | 2026-08-20 |  |  | Project Time Zone | Asia/Ho_Chi_Minh
As of Date | 2026-08-10 |  |  | Project Status | Demo validation
Readiness at a glance
Task completion |  | Open task blockers |  | Residual High / Critical risks |  | Validation failures
Redirect blockers |  | Open launch decisions |  | Validation completion |  | Overall readiness
Working principles
• Keep passwords, API keys, payment details, and unnecessary personal data out of the workbook; use secure evidence links instead.
• A completed migration activity is not an acceptance decision. Validation and sign-off remain separate.
• Use this workbook for project-specific scope, ownership, evidence, and decisions; use current Next-Cart Documentation for operational procedures.
• The purchased migration path is fixed. A different Source Platform → Target Platform direction requires a separate purchased migration.
Note on F12: Paste the exact verified migration-path page. Canonical format: https://next-cart.com/migration/{source_slug}-to-{target_slug}. Do not guess route slugs from display names.
Note on F13: Copy the Entity Points Plan name from the current order or Pricing source rather than relying on a historical plan label.
Note on B14: Current Standard Add-ons: Data Filter; Advanced Data Mapping; Advanced Database Mapping; Data Transformation. Advanced Database Mapping is available only when both Source Platform and Target Platform are Open-Source, and specific field/column compatibility still applies.
Note on B15: Record only approved Customization. A custom field, a database column, or several Standard Add-ons do not automatically require Custom Service.

## Project Plan
Project Plan
Keep work outcome-focused: define what must be true, who owns it, what it depends on, and what evidence closes it.
← Back to Project Overview
Workstream | Task ID | Task / Outcome | Acceptance Criteria / Expected Output | Owner | Approver | Consulted / Support | Milestone / Decision Gate | Dependencies / Related IDs | Start Date | Due Date | Duration (days) | Status | Blocking? | Evidence Link | Notes
Preparation | PREP-01 | Confirm Source Platform and Target Platform access | Required access is available without sharing credentials in the workbook. | Customer Technical Lead | Customer Project Lead | Next-Cart Migration Specialist; Platform Administrator | Access ready | Risks: R-004 | 2026-07-27 | 2026-07-29 |  | Completed | No | secure-link/access-check | Access verified through the supported connection setup displayed by Next-Cart.
Scope | SCOPE-01 | Approve migration scope and intentional exclusions | Required data types, Additional Options, Add-ons, approved Customization, dependencies, exclusions, and Entity Points capacity are documented. | Customer Project Lead | Executive Sponsor | Technical Lead; QA Lead; SEO Lead; Next-Cart Migration Specialist | Scope approval | Depends: PREP-01; Risks: R-003; Validation: VAL-001; VAL-002 | 2026-07-28 | 2026-07-31 |  | Completed | No | secure-link/scope-decision | Data Filter and Advanced Data Mapping are included.
Preparation | AC-01 | Approve acceptance criteria and risk-based validation samples | Each high-risk area has a sample, expected result, blocking condition, owner, and evidence location. | QA Lead | Customer Project Lead | Technical Lead; SEO Lead | Acceptance criteria approved | Depends: SCOPE-01; Risks: R-001; R-002; Validation: VAL-001; VAL-002; VAL-003 | 2026-07-30 | 2026-08-01 |  | Completed | No | secure-link/acceptance-criteria | Privacy-safe evidence rules recorded for Customers and Orders.
Configuration | CFG-01 | Configure Data, Options, Mapping, purchased Add-ons, and approved Customization | Configuration matches the approved scope and the purchased migration service. | Next-Cart Migration Specialist | Customer Project Lead | Technical Lead; QA Lead | Demo configuration ready | Depends: AC-01; Risks: R-001; R-003; Validation: VAL-001; VAL-002 | 2026-08-01 | 2026-08-03 |  | Completed | No | secure-link/config-review | Illustrative Managed Service responsibility; confirm against the actual agreed scope.
Demo Migration | DEMO-01 | Run Demo Migration | Demo activity completes and produces reviewable results for the approved sample scope. | Next-Cart Migration Specialist | Customer Project Lead | QA Lead | Demo results available | Depends: CFG-01; Risks: R-001; R-003; Validation: VAL-001; VAL-002; VAL-003 | 2026-08-03 | 2026-08-03 |  | Completed | No | secure-link/demo-run | Completion is not approval; validation remains separate.
Validation | VALGATE-01 | Validate Demo Migration results | Representative and edge-case records are checked; failures are classified and acceptance decisions are recorded. | QA Lead | Customer Project Lead | Technical Lead; SEO Lead; Next-Cart Migration Specialist | Demo validation decision | Depends: DEMO-01; Risks: R-001; R-002; R-003; Validation: VAL-001; VAL-002; VAL-003; VAL-004 | 2026-08-04 | 2026-08-10 |  | In progress | Yes | secure-link/demo-validation | URL redirect failure remains open.
Decision | DEC-01 | Approve configuration corrections after Demo evidence | Required corrections and accepted target transformations are approved before Full Migration. | Customer Project Lead | Executive Sponsor | QA Lead; Technical Lead | Full Migration configuration approval | Depends: VALGATE-01; Risks: R-001; R-002; Validation: VAL-002; VAL-004 | 2026-08-10 | 2026-08-12 |  | Not started | Yes |  | Blocked until VAL-004 redirect decision and product mapping retest are complete.
Full Migration | FULL-01 | Run Full Migration using the approved configuration | The approved configuration is reviewed and the Full Migration completes with Success, Failed, and Skipped results recorded. | Next-Cart Migration Specialist | Customer Project Lead | QA Lead | Full Migration complete | Depends: DEC-01; Risks: R-005; Validation: VAL-005; VAL-006 | 2026-08-17 | 2026-08-17 |  | Not started | No
Validation | FULLVAL-01 | Validate Full Migration results | High-risk data, relationships, counts, transformations, and target usability meet the approved acceptance criteria. | QA Lead | Customer Project Lead | Technical Lead; Operations Lead | Full Migration sign-off | Depends: FULL-01; Risks: R-001; R-003; R-005; Validation: VAL-005; VAL-006; VAL-007 | 2026-08-18 | 2026-08-19 |  | Not started | No
Launch readiness | LAUNCH-01 | Complete launch-readiness and redirect checks | No unresolved critical blocker remains; required redirects and target-store operational checks pass. | Customer Project Lead | Executive Sponsor | QA Lead; SEO Lead; Operations Lead; Technical Lead | Launch readiness decision | Depends: FULLVAL-01; Risks: R-002; R-004; Validation: VAL-008; RED-001; RED-002 | 2026-08-19 | 2026-08-20 |  | Not started | No
Launch | GO-01 | Record go-live decision | Approver records Approved, Approved with limitations, Rejected, or Deferred with evidence. | Customer Project Lead | Executive Sponsor | QA Lead; SEO Lead; Operations Lead | Go-live | Depends: LAUNCH-01; Risks: R-002; R-004; Validation: VAL-008 | 2026-08-20 | 2026-08-20 |  | Not started | No
Post-launch monitoring | MON-01 | Monitor target-store behavior after launch | Priority customer journeys, Orders, redirects, data changes, and unresolved accepted limitations are reviewed through the planned monitoring window. | Operations Lead | Customer Project Lead | QA Lead; SEO Lead | Post-launch closure | Depends: GO-01; Risks: R-002; R-004; Validation: VAL-009 | 2026-08-20 | 2026-08-24 |  | Not started | No

## Risk Register
Risk Register
Capture future uncertainty before it becomes a defect: state the business consequence, observable trigger, control, owner, and residual exposure.
← Back to Project Overview
Risk ID | Related Task IDs | Business Impact Area | Risk Statement | Likelihood (1-5) | Impact (1-5) | Inherent Score | Inherent Level | Mitigation / Control | Owner | Due Date | Trigger / Early Signal | Status | Residual Likelihood | Residual Impact | Residual Score | Residual Level | Response | Review Date | Evidence Link | Notes
R-001 | VALGATE-01 | Data integrity | Complex Product variants may map into incorrect purchasable combinations, affecting price or SKU selection. | 4 | 5 |  |  | Include highest-complexity Products in Demo validation; confirm options, variants, price, SKU, and purchase behavior before Full Migration. | QA Lead | 2026-08-10 | Demo sample shows missing or mislabeled options. | Mitigating | 2 | 4 |  |  | Reduce | 2026-08-10 | secure-link/risk-R-001
R-002 | LAUNCH-01 | SEO and URLs | Priority source URLs may not reach the approved target destination after launch, causing traffic loss and broken customer journeys. | 3 | 5 |  |  | Create a priority redirect plan, identify implementation ownership, test final destinations, and resolve chains or loops before go-live. | SEO Lead | 2026-08-19 | A priority URL returns 404, an unexpected status, a chain, or an irrelevant destination. | Open | 2 | 5 |  |  | Reduce | 2026-08-10 | secure-link/risk-R-002
R-003 | SCOPE-01 | Service scope | A source application stores business-critical data outside supported standard fields, causing missing meaning in the target store. | 3 | 4 |  |  | Document the field, sample records, dependencies, expected target use, and pass conditions; route unsupported handling to Custom Service assessment. | Technical Lead | 2026-08-12 | Demo evidence shows a required source field is unavailable in standard configuration. | Monitoring | 2 | 3 |  |  | Reduce | 2026-08-10 | secure-link/risk-R-003
R-004 | GO-01 | Target-store readiness | Target-store checkout, email, tax, payment, or fulfillment configuration may fail even when migrated data is correct. | 2 | 5 |  |  | Complete launch-readiness checks and a target-store smoke test with the appropriate platform owners. | Operations Lead | 2026-08-20 | Test order or notification workflow fails. | Open | 1 | 5 |  |  | Reduce | 2026-08-10 | secure-link/risk-R-004
R-005 | FULL-01 | Data integrity | A fresh migration decision may conflict with manual or application-created target records that must remain. | 2 | 5 |  |  | Inventory protected target data and classify the intended action before any destructive clearing or Perform a New Migration decision. | Customer Technical Lead | 2026-08-12 | Protected target records are not included in the replacement plan. | Open | 1 | 5 |  |  | Avoid | 2026-08-10 | secure-link/risk-R-005

## Validation
Validation
Plan the evidence and record the result in the same row. Each validation item should make the sample, pass condition, finding, corrective path, and decision trail easy to reconstruct.
← Back to Project Overview
Validation ID | Activity | Data Area | Related IDs | Validation Objective | Sample / Selection Basis | Record / Reference | Expected Result / Pass Condition | Validator | Planned Date | Actual Result / Finding | Result | Severity | Issue Classification | Blocking? | Corrective Action / Owner | Retest Required? | Retest Result | Evidence Link | Decision ID | Follow-up Status | Notes
VAL-001 | Demo Migration | Products | Run: DEMO-01; Risk: R-001 | Select each option combination and verify purchasable variants. | Highest variant complexity among top-selling Products.; Complex Product | SKU-EX-001 → Target Product / products/example-shirt | Correct option labels, purchasable combinations, price, SKU, and media associations. Pass when every approved combination is usable and no unintended combination is created. | QA Lead | 2026-08-04 | All approved combinations are usable; no unintended combination was found. | Pass | Informational | Target data model | No | Owner: QA Lead | No | Not applicable | secure-link/VAL-001
VAL-002 | Demo Migration | Categories | Run: DEMO-01; Risk: R-001 | Compare representative membership, hierarchy intent, and storefront navigation. | High-revenue source category with nested hierarchy expected to become a target collection structure.; Category hierarchy | CAT-SHOES → Target collection / collections/shoes | Target structure preserves approved business meaning and product discoverability. Pass or Pass with accepted limitations when the approved target model preserves required meaning and usability. | QA Lead | 2026-08-05 | Target collection is flatter than the source hierarchy, but representative Products and approved navigation are correct. | Pass with accepted limitations | Minor | Target data model | No | Record the accepted target-model transformation in DEC-001.; Owner: Customer Project Lead | No | Not applicable | secure-link/VAL-002 | DEC-001 |  | Accepted limitation requires final sign-off evidence.
VAL-003 | Demo Migration | Customers | Run: DEMO-01; Risk: R-003 | Verify required fields, addresses, group mapping where supported, and target account usability expectations. | Representative Customer with two addresses; evidence uses masked identifier.; Customer relationship | CUS-***-1042 → Target Customer / masked internal ID | Required migrated fields and relationships are present without exposing credentials. Pass when the approved fields and relationships are usable; password behavior follows platform capability. | QA Lead | 2026-08-06 | Required fields and both addresses are present; Order association is correct. | Pass | Informational | Target data model | No | Owner: QA Lead | No | Not applicable | secure-link/VAL-003
VAL-004 | Demo Migration | URLs and redirects | Run: DEMO-01; Risk: R-002 | Test source URL or path, observed status, final destination, and chain/loop behavior. | Top organic landing page scheduled for a target path change.; Priority URL | /old-running-shoes → /collections/running-shoes | Required routing reaches the relevant approved destination without a loop. Pass when intended behavior is implemented and the final destination is correct. | SEO Lead | 2026-08-07 | The source path returns 404 in target staging. | Fail | High | Target-store presentation | Yes | Assign redirect implementation to the target-platform owner; retest RED-001 before launch approval.; Owner: SEO Lead | Yes | Not tested | secure-link/VAL-004 | DEC-004 |  | Launch blocking until corrected.
VAL-005 | Full Migration | Orders | Run: FULL-01; Risk: R-003 | Compare key commercial values and support usability. | Representative completed Order with discount, tax, shipping, Customer association, and multiple line items.; Order edge case | ORD-***-8842 → Target Order / masked internal ID | Items, totals, statuses, associations, and approved identifiers are plausible and usable. Pass when the record supports the approved operational use despite allowed target-model differences. | QA Lead | 2026-08-18 |  | Not tested |  |  | To be confirmed |  |  | Not tested | secure-link/VAL-005
VAL-006 | Launch readiness | Checkout | Run: LAUNCH-01; Risk: R-004 | Complete a test order and verify confirmation and operational notification. | Critical customer journey independent of migration-result correctness.; Smoke test | TEST-ORDER-01 → Target production checkout | The target-store workflow completes according to the launch plan. Pass when the approved payment/test method and notifications complete. | Operations Lead | 2026-08-20 |  | Not tested |  |  | To be confirmed |  |  | Not tested | secure-link/VAL-006 |  |  | Launch-readiness check, not a data-migration validation record.

## Redirects
Redirects
Track only URL continuity that matters to the migration or launch. Record the intended destination, ownership, observed behavior, and any approved exception in one place.
← Back to Project Overview
Redirect ID | Related Validation / Decision IDs | Source URL or Path | Target URL or Path | Content Type | Priority | Redirect Required? | Intended Behavior / Method | Owner | Environment | Implemented? | Tested? | HTTP Status | Final Destination | Chain / Loop | Test Result | Test Date | Evidence / Exception | Readiness | Notes
RED-001 | VAL-004; Must be corrected before launch. | /old-running-shoes | /collections/running-shoes | Category / collection | Critical | Yes | Target-native redirect | SEO Lead | Target staging | No | Yes | 404 | /old-running-shoes | Not applicable | Fail | 2026-08-07 | secure-link/RED-001; Must be corrected before launch.
RED-002 | VAL-007 | /products/example-shirt | /products/example-shirt | Product | High | No | Preserved URL | Target Platform Administrator | Target staging | Yes | Yes | 200 | /products/example-shirt | Not applicable | Pass | 2026-08-09 | secure-link/RED-002
RED-003 |  | /blog/size-guide | /pages/size-guide | CMS / Blog | Medium | Yes | Manual redirect | SEO Lead | Target staging | Yes | Yes | 301 | /pages/size-guide | No chain or loop | Pass | 2026-08-09 | secure-link/RED-003
RED-004 | Accepted retirement recorded in DEC-003. | /campaign/summer-2024 |  | Campaign | Low | No | Accepted no redirect | Marketing Lead | External routing | No | No |  |  | Not applicable | Not applicable | 2026-08-09 | secure-link/RED-004; Accepted retirement recorded in DEC-003.

## Decisions & Sign-off
Decisions and Sign-off
Make scope choices, accepted limitations, risk treatment, and launch approval explicit. A decision is closed only when the owner, approver, evidence, and conditions are complete.
← Back to Project Overview
Decision ID | Decision Type | Related IDs | Decision / Scope | Rationale | Outcome | Conditions / Accepted Limitations | Decision Owner | Approver | Decision Date | Evidence Link | Review / Expiry Date | Launch Blocking? | Review Status | Notes
DEC-001 | Accepted limitation | VAL-002; R-001 | Accept a flatter target collection structure for the Shoes category. | The target data model cannot reproduce the source hierarchy exactly, but approved Product membership, navigation, and discoverability are preserved. | Approved with limitations | Monitor navigation analytics after launch and retain validation evidence. | Customer Project Lead | Executive Sponsor | 2026-08-10 | secure-link/DEC-001 | 2026-08-24 | No
DEC-002 | Mapping | VAL-001; R-001; CFG-01 | Approve the corrected Product option and variant mapping for Full Migration. | Demo retest confirms approved option labels, purchasable combinations, price, and SKU behavior. | Pending |  | Customer Project Lead | Executive Sponsor |  |  | 2026-08-12 | Yes |  | Awaiting product mapping retest.
DEC-003 | Exclusion | RED-004 | Retire the obsolete summer campaign URL without a redirect. | The campaign has no continuing content, traffic, revenue, or contractual value. | Approved | Retain the decision record and monitor 404 reports after launch. | Marketing Lead | Executive Sponsor | 2026-08-09 | secure-link/DEC-003 | 2026-08-24 | No
DEC-004 | Launch readiness | LAUNCH-01; VAL-004; RED-001; R-002 | Approve or defer go-live after the priority redirect defect is retested. | Launch requires the priority URL to reach the approved target destination without a chain or loop. | Pending |  | Customer Project Lead | Executive Sponsor |  |  | 2026-08-20 | Yes

## _Lists (hidden)
TaskStatusList | YesNoTbdList | YesNoList | ServiceTypeList | ProjectStatusList | WorkstreamList | RiskStatusList | RiskResponseList | BusinessImpactList | ValidationActivityList | DataAreaList | ValidationResultList | IssueSeverityList | IssueClassificationList | RetestResultList | RedirectPriorityList | RedirectMethodList | EnvironmentList | RedirectTestResultList | ChainLoopList | DecisionTypeList | DecisionOutcomeList | LaunchBlockingList
Not started | Yes | Yes | Standard Service | Planning | Preparation | Open | Reduce | Data integrity | Demo Migration | Taxes | Pass | Informational | Source access | Pass | Critical | Preserved URL | Source production | Pass | No chain or loop | Scope | Pending | Yes
In progress | No | No | Managed Service | Preparing | Access | Monitoring | Accept | Customer experience | Full Migration | Manufacturers | Pass with accepted limitations | Minor | Unsupported migration-path behavior | Fail | High | Target-native redirect | Target staging | Fail | Chain detected | Exclusion | Approved | No
Blocked | To be confirmed |  | Custom Service | Configuring | Scope | Mitigating | Avoid | SEO and URLs | Continue the Migration with the Last Used Configuration | Categories | Fail | Moderate | Configuration | Not tested | Medium | Manual redirect | Target production | Not tested | Loop detected | Mapping | Approved with limitations
Completed |  |  |  | Demo validation | Configuration | Accepted | Transfer | Orders and operations | Continue the Migration with a New Configuration | Products | Not applicable | High | Mapping | Not applicable | Low | External routing | External routing | Not applicable | Not tested | Additional Option | Rejected
Deferred |  |  |  | Full Migration | Demo Migration | Closed | Close | Timeline | Perform a New Migration | Customers | Not tested | Critical | Add-on |  |  | Accepted no redirect |  |  | Not applicable | Add-on | Deferred
Not applicable |  |  |  | Full Migration validation | Validation |  |  | Compliance and privacy | Launch readiness | Orders |  |  | Approved Customization | [6 empty] | Approved Customization | Not applicable
|  |  |  | Launch readiness | Decision |  |  | Integration | Post-launch monitoring | Reviews |  |  | Target data model | [6 empty] | Accepted limitation
|  |  |  | Launched | Full Migration |  |  | Target-store readiness |  | Coupons |  |  | Target-store presentation | [6 empty] | Risk treatment
|  |  |  | Post-launch monitoring | Launch readiness |  |  | Service scope |  | CMS Pages |  |  | External system | [6 empty] | Full Migration
|  |  |  | Closed | Launch |  |  |  |  | Blog Posts |  |  | Data quality | [6 empty] | Launch readiness
|  |  |  | On hold | Post-launch monitoring |  |  |  |  | Images and media |  |  | Other | [6 empty] | Go-live
[5 empty] | Custom Service |  |  |  |  | URLs and redirects | [9 empty] | Post-launch closure
Checkout
Storefront navigation
Target configuration