## Project Overview
Next-Cart Migration Project Toolkit
Bring scope, owners, risk, evidence, URL continuity, and launch decisions into one project view so the team can see what is ready and what still needs proof.
Start with the migration path, then work outward: plan accountable work, surface uncertainty early, validate evidence, protect priority URLs, and close launch decisions explicitly. Use current Next-Cart Documentation for procedures and exact service behavior; record project-specific choices and evidence here.
Plan | Risks | Validation | Redirects | Decisions | Overview / readiness
Project identity and migration
Project Name |  |  |  | Project ID
Source Platform |  |  |  | Target Platform
Migration Path |  |  |  | Supported Data Reference
Migration Service |  |  |  | Entity Points Plan
Purchased Add-ons |  |  |  | Purchased Entity Points
Approved Customization |  |  |  | Service Expiry
Project Owner |  |  |  | Launch Approver
Evidence Repository |  |  |  | Next-Cart Contact
Milestones and control
Demo Migration planned date |  |  |  | Full Migration planned date
Launch window |  |  |  | Project Time Zone
As of Date |  |  |  | Project Status
Readiness at a glance
Task completion |  | Open task blockers |  | Residual High / Critical risks |  | Validation failures
Redirect blockers |  | Open launch decisions |  | Validation completion |  | Overall readiness
Working principles
• Keep passwords, API keys, payment details, and unnecessary personal data out of the workbook; use secure evidence links instead.
• A completed migration activity is not an acceptance decision. Validation and sign-off remain separate.
• Use this workbook for project-specific scope, ownership, evidence, and decisions; use current Next-Cart Documentation for operational procedures.
• The purchased migration path is fixed. A different Source Platform → Target Platform direction requires a separate purchased migration.
Note on F12: Paste the exact verified migration-path page. Canonical format: https://next-cart.com/migration/{source_slug}-to-{target_slug}. Do not guess route slugs from display names.
Note on F13: Copy the Entity Points Plan name from the current order or Pricing source rather than relying on a historical plan label.
Note on B14: Current Standard Add-ons: Data Filter; Advanced Data Mapping; Advanced Database Mapping; Data Transformation. Advanced Database Mapping is available only when both Source Platform and Target Platform are Open-Source, and specific field/column compatibility still applies.
Note on B15: Record only approved Customization. A custom field, a database column, or several Standard Add-ons do not automatically require Custom Service.

## Project Plan
Project Plan
Keep work outcome-focused: define what must be true, who owns it, what it depends on, and what evidence closes it.
← Back to Project Overview
Workstream | Task ID | Task / Outcome | Acceptance Criteria / Expected Output | Owner | Approver | Consulted / Support | Milestone / Decision Gate | Dependencies / Related IDs | Start Date | Due Date | Duration (days) | Status | Blocking? | Evidence Link | Notes

## Risk Register
Risk Register
Capture future uncertainty before it becomes a defect: state the business consequence, observable trigger, control, owner, and residual exposure.
← Back to Project Overview
Risk ID | Related Task IDs | Business Impact Area | Risk Statement | Likelihood (1-5) | Impact (1-5) | Inherent Score | Inherent Level | Mitigation / Control | Owner | Due Date | Trigger / Early Signal | Status | Residual Likelihood | Residual Impact | Residual Score | Residual Level | Response | Review Date | Evidence Link | Notes

## Validation
Validation
Plan the evidence and record the result in the same row. Each validation item should make the sample, pass condition, finding, corrective path, and decision trail easy to reconstruct.
← Back to Project Overview
Validation ID | Activity | Data Area | Related IDs | Validation Objective | Sample / Selection Basis | Record / Reference | Expected Result / Pass Condition | Validator | Planned Date | Actual Result / Finding | Result | Severity | Issue Classification | Blocking? | Corrective Action / Owner | Retest Required? | Retest Result | Evidence Link | Decision ID | Follow-up Status | Notes

## Redirects
Redirects
Track only URL continuity that matters to the migration or launch. Record the intended destination, ownership, observed behavior, and any approved exception in one place.
← Back to Project Overview
Redirect ID | Related Validation / Decision IDs | Source URL or Path | Target URL or Path | Content Type | Priority | Redirect Required? | Intended Behavior / Method | Owner | Environment | Implemented? | Tested? | HTTP Status | Final Destination | Chain / Loop | Test Result | Test Date | Evidence / Exception | Readiness | Notes

## Decisions & Sign-off
Decisions and Sign-off
Make scope choices, accepted limitations, risk treatment, and launch approval explicit. A decision is closed only when the owner, approver, evidence, and conditions are complete.
← Back to Project Overview
Decision ID | Decision Type | Related IDs | Decision / Scope | Rationale | Outcome | Conditions / Accepted Limitations | Decision Owner | Approver | Decision Date | Evidence Link | Review / Expiry Date | Launch Blocking? | Review Status | Notes

## _Lists (hidden)
TaskStatusList | YesNoTbdList | YesNoList | ServiceTypeList | ProjectStatusList | WorkstreamList | RiskStatusList | RiskResponseList | BusinessImpactList | ValidationActivityList | DataAreaList | ValidationResultList | IssueSeverityList | IssueClassificationList | RetestResultList | RedirectPriorityList | RedirectMethodList | EnvironmentList | RedirectTestResultList | ChainLoopList | DecisionTypeList | DecisionOutcomeList | LaunchBlockingList
Not started | Yes | Yes | Standard Service | Planning | Preparation | Open | Reduce | Data integrity | Demo Migration | Taxes | Pass | Informational | Source access | Pass | Critical | Preserved URL | Source production | Pass | No chain or loop | Scope | Pending | Yes
In progress | No | No | Managed Service | Preparing | Access | Monitoring | Accept | Customer experience | Full Migration | Manufacturers | Pass with accepted limitations | Minor | Unsupported migration-path behavior | Fail | High | Target-native redirect | Target staging | Fail | Chain detected | Exclusion | Approved | No
Blocked | To be confirmed |  | Custom Service | Configuring | Scope | Mitigating | Avoid | SEO and URLs | Continue the Migration with the Last Used Configuration | Categories | Fail | Moderate | Configuration | Not tested | Medium | Manual redirect | Target production | Not tested | Loop detected | Mapping | Approved with limitations
Completed |  |  |  | Demo validation | Configuration | Accepted | Transfer | Orders and operations | Continue the Migration with a New Configuration | Products | Not applicable | High | Mapping | Not applicable | Low | External routing | External routing | Not applicable | Not tested | Additional Option | Rejected
Deferred |  |  |  | Full Migration | Demo Migration | Closed | Close | Timeline | Perform a New Migration | Customers | Not tested | Critical | Add-on |  |  | Accepted no redirect |  |  | Not applicable | Add-on | Deferred
Not applicable |  |  |  | Full Migration validation | Validation |  |  | Compliance and privacy | Launch readiness | Orders |  |  | Approved Customization | [6 empty] | Approved Customization | Not applicable
|  |  |  | Launch readiness | Decision |  |  | Integration | Post-launch monitoring | Reviews |  |  | Target data model | [6 empty] | Accepted limitation
|  |  |  | Launched | Full Migration |  |  | Target-store readiness |  | Coupons |  |  | Target-store presentation | [6 empty] | Risk treatment
|  |  |  | Post-launch monitoring | Launch readiness |  |  | Service scope |  | CMS Pages |  |  | External system | [6 empty] | Full Migration
|  |  |  | Closed | Launch |  |  |  |  | Blog Posts |  |  | Data quality | [6 empty] | Launch readiness
|  |  |  | On hold | Post-launch monitoring |  |  |  |  | Images and media |  |  | Other | [6 empty] | Go-live
[5 empty] | Custom Service |  |  |  |  | URLs and redirects | [9 empty] | Post-launch closure
Checkout
Storefront navigation
Target configuration